## Capston_project_plan
Project List | Goal | Month | [17 empty] | Progress
|  | November | [5 empty] | December
|  | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Kickoff | Plan | November 25: Meeting
Actual | bar: November 25
Project Declaration | Plan | November 26: Meeting
Actual | bar: November 26
Download and understand project goals | Plan | bar: November 26 to November 27
Actual | bar: November 26 to November 28
Data Preparation/Exploratory Data Analysis | Plan | [18 empty] | 4 days behind | bar: November 28 to December 1
Actual | bar: November 27 to December 5
Milestone 1 (Cleaned Dataset) | Plan | December 2: Meeting
| Actual | December 4: Meeting
Train reference model | Plan | [18 empty] | 1 day behind | bar: December 1 to December 4
Actual | bar: December 3 to December 4
test reference model | Plan | [18 empty] | 1 day behind | bar: December 2 to December 5
Actual | bar: December 3 to December 5
train advanced model | Plan | December 5: Meeting; December 6: Meeting | 1 day behind
Actual | bar: December 4 to December 7
test advanced model | Plan | bar: December 5 to December 7
Actual | bar: December 6 to December 7
finalize model | Plan | bar: December 6 to December 7
| Actual | December 8: Meeting
Lift Analysis | Plan | [18 empty] | 1 day behind | bar: December 7 to December 8
Actual | bar: December 8
Milestone 2 (Modeling) | Plan | bar: December 8
Actual | bar: December 9
Create Presentation | Plan | December 10: Meeting | 1 day behind
Actual | bar: December 10 to December 11
Milestone 3 (Presentation) | Plan | December 11: Meeting
Actual | bar: December 11
Delivery | Actual | December 12: Delivery
Actual
Remarks: | numbers in the cell = meeting